## Estimation Record
ESTIMATION RECORD - version 1.0
|  |  |  | Expert 1 | Expert 2 | Expert 3 | Expert 4
|  | Size Measure | Size | Effort (person/hours) |  |  |  | Final (Fibonacci)
Requirements | Definition of Personas | # roles | 5 | 2 | 1 | 1 | 1 | 2
| Definition of Scope | # attributes | 10 | 1 | 1 | 1 | 1 | 1
| User Stories | # requirements | 5 | 1 | 2 | 1 | 1 | 2
Config Mgmt | CI List | # CI Items | 10 | 2 | 1 | 1 | 1 | 2
Estimation | Estimation Record | # activities | 1 | 3 | 1 | 1 | 1 | 3
Design | Diagrams | # UML diagrams | 1 | 1 | 3 | 1 | 1 | 3
|  | # State Diagrams | 1 | 1 | 1 | 2 | 2 | 2
| Components Interaction Diagram | # Interaction Diagrams | 1 | 1 | 1 | 2 | 2 | 2
Coding | Code | #Lines | 1000 | 0 | 0 | 40 | 30 | 55
Peer Reviews | Issues | # issues | 5 | 1 | 1 | 2 | 2 | 2
Implementation | System | # Wireframes | 5 | 2 | 4 | 2 | 2 | 5
Test Design | Test Cases | # test cases | 10 | 1 | 3 | 5 | 5 | 5
Test Execution | Defects/Bugs | # defects | 5 | 3 | 3 | 3 | 3 | 3