## Est Record
ESTIMATION RECORD - version 2.2
|  |  |  | Expert 1 | Expert 2 | Expert 3 | Expert 4
|  | Size Measure | Size | Effort (person/hours) |  |  |  | Final (Fibonacci)
Requirements | Definition of Personas | # personas | 5 | 3 | 4 | 5 | 3 | 5
| Definition of Scope | # attributes | 10 | 4 | 4 | 4 | 4 | 5
| User Stories | # requirements | 11 | 7 | 6 | 6 | 6 | 8
Config Mgmt | CI List | # CI Items | 20 | 6 | 5 | 6 | 4 | 8
Estimation | Estimation Record | # activities | 1 | 5 | 5 | 5 | 5 | 5
Design | Diagrams | # Use Case diagrams | 1 | 10 | 12 | 10 | 10 | 13
| Diagrams | # State Diagrams | 4 | 8 | 8 | 7 | 7 | 8
| Diagrams | # Components Interaction Diagrams | 1 | 7 | 7 | 6 | 6 | 8
Coding | Code | #Lines | 4000 | 40 | 40 | 70 | 70 | 89
Peer Reviews | Issues | # issues | 2 | 6 | 6 | 7 | 7 | 8
Implementation | System | # Wireframes | 6 | 4 | 4 | 4 | 3 | 5
Test Design | Test Cases | # test cases | 6 | 7 | 7 | 8 | 7 | 8
Test Execution | Defects/Bugs | # defects | 5 | 4 | 4 | 4 | 5 | 5
Total | [7 empty] | 175